## 0-Client Quote
FORGE Estimation — Client Quote (AFP × $/FP)
A. PRICING PARAMETERS (Stack Factor × Org Factor × $/FP)
Parameter | Value | Description / Source
Stack Factor (base tier) | 1 | Standard single stack: Django + HTMX + SQLite (no legacy, no enterprise platform)
Stack Factor modifiers | 0 | No modifiers: greenfield project, no on-prem, no legacy integration, no mobile
Stack Factor TOTAL | 1 | Effective Stack Factor = 1.00
Org Factor | 0.8 | Solo developer, personal project, flat structure — startup-like (0.80)
$/FP Rate | 250 | SEED $250/FP — update after 3 sprints via EST-08. Includes ~3× markup over API cost.
$/FP Status | SEED | Change to CALIBRATED after 3 sprints of actuals (EST-08 sprint close)
B. QUOTE SUMMARY (AFP = FP × Stack × Org)
Line Item | FP | Stack × Org Adj. | AFP | $ Total (AFP × $/FP)
Sprint 0 — Project Setup (BSP + DSP) | 0 |  | 0 | 0
Feature Delivery (from Scenario List) | 56 |  | 44.8 | 11200
PROJECT TOTAL | 56 |  | 44.8 | 11200
C. DELIVERY COMMITMENT BANDS (from Monte Carlo — EST-07)
Percentile | AFP (adj. for band) | $ Total | Duration (days) | Est. Completion Date
P10 | 35.8 | 8950 | 2.2
P50 — Median | 44.8 | 11200 | 2.7
P80 — Planning Target ★ | 56 | 14000 | 3.4
P95 — Conservative | 67.2 | 16800 | 4.1
D. NOTES
Calibration context: Mimir MVP v1 estimated 114.5 SP / 6,433K tokens → actual VF = 0.40×.
Root cause: scenario count used as sizing proxy (Playbooks VF=0.19×). v2 fix: reuse discount applied.
New SP = 58 (−49%). Token budget: 4,060K exp. VF target: 0.9–1.3× (Activities anchor 1.21×).
$/FP SEED $250 — calibrate after Sprint 1 via EST-08. Sprint 0 not included (project bootstrapped).

## 1-Setup
FORGE Estimation Template — Setup & Calibration
A. PROJECT PARAMETERS
Project Name | Mimir FOB — MVP Estimation v2 (calibrated sizing)
Sprint Duration (days) | 1
Daily Token Throughput (K tokens) | 1500
AI Model | Claude Sonnet 4.x
Productivity Adjustment Factor (PAF) | 1.35
Rework Surcharge (%) | 0.12
Combined Risk Multiplier (ECF × TCF — internal) | 0.87
Estimation Phase | Architecture Complete (SAO.md exists)
Convergence Min Multiplier | 0.8
Convergence Max Multiplier | 1.25
B. REFERENCE STORY BASELINES (SP = internal effort ¦ FP = client deliverable)
Size | SP (internal) | FP weight (client) | K Min (K tok) | K Exp (K tok) | K Max (K tok) | Status | Source / Notes
XS | 0.5 | 0.5 | 12 | 22 | 36 | SEED | Simple modal, inline form, config entry
S | 1 | 1 | 25 | 45 | 72 | SEED | Single CRUD screen, service+repo+view+tests
M | 2 | 2 | 60 | 100 | 160 | SEED | Full BPE cycle, first-time entity or novel component
L | 5 | 3 | 155 | 250 | 410 | SEED | Cross-cutting or network integration (e.g. SYNC)
XL | 8 | 5 | 275 | 440 | 720 | SEED | Complex subsystem — not used in v2 Mimir estimate
SP drives internal token budget (Est. = SP × K × ECF×TCF). FP weights drive client AFP (AFP = Σ FP × Stack × Org). L=5 SP / 3 FP and XL=8 SP / 5 FP — complex work ≠ proportional client value.
C. SPRINT CAPACITY PLANNING
Sprint # | SP Capacity | Token Budget (K, expected) | Token Budget (K, max) | Notes
1 | 20
2 | 20
3 | 20
4 | 20
5 | 20
6 | 20
7 | 20
8 | 20
20
20

## 2-Scenario List
Scenario List — Level 1 T-Shirt Sizing (SP = internal ¦ FP = client)
Scenario ID | Feature | Act/Group | Scenario Description | Size | SP (internal) | FP weight (client) | K Min | K Exp | K Max | Adj K Min | Adj K Exp | Adj K Max | Sprint # | Notes / Assumptions
ACT0-AUTH-01 | authentication.feature | Act 0 | Login, logout, session management (first auth model) | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 1 | v2: First novel entity with auth logic; appropriate S
ACT0-NAV-01 | navigation.feature | Act 0 | Main nav, breadcrumbs, global search | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 1 | v2: Config/template-heavy, minimal model work → v2 rule: config=XS
ACT0-ONBOARD-01 | onboarding.feature | Act 0 | First-run setup, local user creation | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 1 | v2: First-run wizard with model → S appropriate
PB-LIST-01 | playbooks-list-find | Act 2 | Playbooks list+search+filter, dashboard entry | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 1 | v2: First list view with search — novel enough for M (not L; search reuses Django ORM)
PB-CREATE-01 | playbooks-create | Act 2 | Create new playbook wizard (DRAFT flow) | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 1 | v2: First create with wizard UX — M; not L since DRAFT flag is simple state
PB-VIEW-01 | playbooks-view | Act 2 | Playbook detail, workflow tab, metadata | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 2 | v2: Detail view with related tab — M; reuses pattern after PB-CREATE
PB-EDIT-01 | playbooks-edit | Act 2 | Edit playbook metadata, status management | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 2 | v2: Edit form reuses create pattern → v2 rule: Nth CRUD entity = S
PB-DELETE-01 | playbooks-delete | Act 2 | Delete confirmation modal, dependency check | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 2 | v2: Delete modal with dep-check — S (check adds minor complexity over pure XS)
PB-VERSION-01 | playbooks-versioning | Act 2 | Draft→Release versioning, version history | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 2 | v2: First versioning feature — novel state machine → M
WF-LIST-01 | workflows-list-find | Act 3 | Workflows list inside playbook, search | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 2 | v2: Reuses PB list pattern → v2 rule: 2nd CRUD entity of list type = S
WF-CREATE-01 | workflows-create | Act 3 | Create workflow, phase org toggle | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 2 | v2: Reuses PB create pattern → S
WF-VIEW-01 | workflows-view | Act 3 | Workflow detail, Graphviz activity diagram | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 3 | v2: Graphviz rendering is a novel component → M
WF-EDIT-01 | workflows-edit | Act 3 | Edit workflow name/description | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Simple edit form, full pattern reuse → XS
WF-DELETE-01 | workflows-delete | Act 3 | Delete workflow confirmation | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Reuses delete modal pattern → XS
WF-EXPORT-01 | workflows-export-import | Act 3 | Export/import workflow to/from local .md | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 3 | v2: File I/O is novel — first export feature → M
PH-LIST-01 | phases-list-find | Act 4 | Phases list inside workflow | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Nested list, reuses pattern, no search needed → XS
PH-CREATE-01 | phases-create | Act 4 | Create phase inline form | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Inline form, no service layer → XS
PH-VIEW-01 | phases-view | Act 4 | Phase detail, activities in phase | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Simple container view → XS
PH-EDIT-01 | phases-edit | Act 4 | Edit phase name/order | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Edit inline form → XS
PH-DELETE-01 | phases-delete | Act 4 | Delete phase, reassign activities | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 3 | v2: Reassign logic adds minor work but still XS
ACT-LIST-01 | activities-list-find | Act 5 | Activities list, grouped by phase, search | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 4 | v2: Grouped-by-phase display is a novel layout → M (VF=1.21× confirmed accurate for Activities)
ACT-CREATE-01 | activities-create | Act 5 | Create activity with Markdown guidance | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 4 | v2: New model with Markdown field — S
ACT-VIEW-01 | activities-view | Act 5 | Activity detail, Mermaid rendering, deps | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 4 | v2: Mermaid component is new but small — S
ACT-EDIT-01 | activities-edit | Act 5 | Edit activity guidance, phase, order | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 4 | v2: Reuses edit pattern → XS
ACT-DELETE-01 | activities-delete | Act 5 | Delete activity confirmation | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 4 | v2: Reuses delete pattern → XS
ART-LIST-01 | artifacts-list-find | Act 6 | Artifacts list, filter by type | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 4 | v2: Reuses list pattern, type filter is minor → S
ART-CREATE-01 | artifacts-create | Act 6 | Create artifact with type, description | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 4 | v2: Reuses create pattern → XS
ART-VIEW-01 | artifacts-view | Act 6 | Artifact detail, linked activities | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 4 | v2: M2M display in view — S (not M; display is read-only)
ART-EDIT-01 | artifacts-edit | Act 6 | Edit artifact metadata | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses edit pattern → XS
ART-DELETE-01 | artifacts-delete | Act 6 | Delete artifact, unlink from activities | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses delete pattern → XS
ART-FLOW-01 | artifacts-flow | Act 6 | Artifact I/O flow: link/unlink producer-consumer | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 5 | v2: Novel producer-consumer M2M linking UI → M (was XL — over-sized; no external API involved)
AG-LIST-01 | agents-list-find | Act 7 | Agents list, search by name/type | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses list pattern → XS
AG-CREATE-01 | agents-create | Act 7 | Create agent (name, type, config) | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Simple form → XS
AG-VIEW-01 | agents-view | Act 7 | Agent detail, linked activities | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Read-only view, reuses pattern → XS
AG-EDIT-01 | agents-edit | Act 7 | Edit agent config | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses edit pattern → XS
AG-DELETE-01 | agents-delete | Act 7 | Delete agent confirmation | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses delete pattern → XS
SK-LIST-01 | skills-list-find | Act 8 | Skills list, filter by type | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses list pattern → XS
SK-CREATE-01 | skills-create | Act 8 | Create skill, link to activity | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 5 | v2: Reuses create pattern → XS
SK-VIEW-01 | skills-view | Act 8 | Skill detail with guidance content | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 6 | v2: Reuses view pattern → XS
SK-EDIT-01 | skills-edit | Act 8 | Edit skill content | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 6 | v2: Reuses edit pattern → XS
SK-DELETE-01 | skills-delete | Act 8 | Delete skill confirmation | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 6 | v2: Reuses delete pattern → XS
SK-LINK-01 | skills-link | Act 8 | Link/unlink skill ↔ activity M2M | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 6 | v2: M2M linking is semi-novel (first explicit link/unlink flow) → S
PIP-CREATE-01 | pips-create | Act 9 | Create PIP from activity/workflow context | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 6 | v2: Small contextual form, reuses pattern → XS
PIP-MANAGE-01 | pips-manage | Act 9 | Review, approve, reject PIPs; PIP list | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 6 | v2: Status state machine is semi-novel → S
IE-01 | import-export | Act 10 | Upload/validate/import playbook package | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 6 | v2: File handling + validation + import logic — novel enough for M
FAM-01 | family-management | Act 11 | Family access control, member management | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 7 | v2: First access-control feature — M (novel permissions model)
SYNC-01 | sync-scenarios | Act 12 | Download/sync from HOMEBASE, conflict handling | L | 5 | 3 | 155 | 250 | 410 | 573 | 1088 | 2051 | 7 | v2: Network protocol + conflict resolution — genuinely complex → L (kept from v1)
MCP-BASE-01 | mcp-integration | Act 13 | MCP server setup, auth token, @tools listing | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 7 | v2: First MCP server — novel integration setup → M
MCP-PB-01 | mcp-playbooks | Act 13 | MCP CRUD for playbooks (5 tools) | M | 2 | 2 | 60 | 100 | 160 | 89 | 174 | 320 | 7 | v2: First MCP tool set — novel protocol bridge → M (was L; reuses existing service layer)
MCP-WF-01 | mcp-workflows | Act 13 | MCP CRUD for workflows (5 tools) | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 7 | v2: Reuses MCP handler pattern from PB → v2: 2nd MCP entity = S
MCP-ACT-01 | mcp-activities | Act 13 | MCP CRUD for activities (6 tools + deps) | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 8 | v2: Reuses MCP pattern; deps add minor complexity → S
MCP-AG-01 | mcp-agents | Act 13 | MCP CRUD for agents (5 tools) | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 8 | v2: Simple entity, full pattern reuse → XS
MCP-SK-01 | mcp-skills | Act 13 | MCP CRUD+link for skills (6 tools) | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 8 | v2: Reuses MCP pattern; link tool adds minor work → S
SET-01 | settings | Act 14 | App settings: theme, token budget, API keys | XS | 0.5 | 0.5 | 12 | 22 | 36 | 4 | 10 | 18 | 8 | v2: Config/settings page — v2 rule: config = XS
ERR-01 | error-recovery | Act 15 | Global error handling, retry, offline states | S | 1 | 1 | 25 | 45 | 72 | 18 | 39 | 72 | 8 | v2: Error UI patterns — S (some novel state management)
TOTALS |  |  |  |  | 58 | 56 |  |  |  | 2033 | 4060 | 7511
Total FP (col G) = 56.0 FP → AFP = 56.0 × 1.0 × 0.8 = 44.8 AFP → Quote = $11,200

## 3-ECF
Environmental Complexity Factors (ECF) — INTERNAL
INTERNAL: ECF feeds the internal combined multiplier (token budget). Never shown to client.
# | Factor | Weight | Rating (0–5) | Weighted | Notes
E1 | Familiarity with AI model/tooling | 1.5 | 4 |  | Experienced with Claude Sonnet via mature BPE workflow
E2 | Part-time participation / context switching | -1 | 2 |  | Solo dev — occasional interruptions
E3 | Analyst / prompt engineering experience | 0.5 | 4 |  | BPE prompts are mature and proven
E4 | Lead developer application experience | 0.5 | 4 |  | Denis knows Django well
E5 | Motivation of team | 1 | 5 |  | Personal project — very high motivation
E6 | Stability of requirements | 2 | 4 |  | BDD scenarios fully written, SAO.md complete
E7 | Part-time users / product owners | -1 | 5 |  | Denis IS the product owner, available full-time
E8 | Difficulty of stack / language | -1 | 4 |  | Django+HTMX+SQLite — well-known, low friction stack
AI-Specific Extension Factors
A1 | AI model tier (Opus=5, Sonnet=3, Haiku=1) | 0.8 | 3 |  | Claude Sonnet = Tier 3
A2 | Prompt maturity (mature=5, first use=1) | 0.6 | 4 |  | BPE prompts mature and proven across prior projects
A3 | Hallucination risk (low risk=5, high risk=1) | -0.5 | 4 |  | Django domain well-known to model (low hallucination risk)
A4 | Context window pressure (large ctx=5, small=1) | -0.4 | 3 |  | Context pressure moderate — feature files fit in window
A5 | AI code rework rate (41% baseline = rating 3) | -0.6 | 3 |  | 41% churn baseline — no specific mitigation yet
ECF Base
AI Adjustment
ECF Final = Base × AI Adj
→ ECF Final × TCF Final = Combined Multiplier → paste into '1-Setup'!B10

## 4-TCF
Technical Complexity Factors (TCF) — INTERNAL
INTERNAL: TCF feeds the combined multiplier. Client-facing complexity is captured by Stack Factor (Tab 0).
# | Factor | Weight | Rating (0–5) | Weighted | Notes
T1 | Distributed system / microservices | 2 | 1 |  | Monolith — Django+SQLite, not distributed
T2 | Response time / performance requirements | 1 | 2 |  | Standard web response times, no SLA
T3 | End-user efficiency (optimized UX) | 1 | 3 |  | Developer tool — UX important but not novice-targeted
T4 | Complex internal processing / algorithms | 1 | 2 |  | Mostly CRUD with some graph logic (Graphviz)
T5 | Code reusability requirement | 1 | 4 |  | DRY/reusability is a first-class design goal (services, repos)
T6 | Easy to install / deploy | 0.5 | 3 |  | Docker container — reasonable install
T7 | Easy to use (usability target) | 0.5 | 3 |  | Developer tool — usability matters for productivity
T8 | Portability across platforms | 2 | 2 |  | Docker container + local venv — macOS/Linux only
T9 | Maintainability / easy to change | 1 | 5 |  | Maintainability is top priority — methodology evolves sprint to sprint
T10 | Concurrent use / multi-user | 1 | 1 |  | Single-user desktop application
T11 | Security features | 1 | 2 |  | Local app — no sensitive data, no external auth
T12 | Third-party API / direct access | 1 | 3 |  | MCP protocol integration (Act 13)
T13 | Special user training required | 1 | 2 |  | Developer tool — minimal onboarding required
TCF Final
ECF Final (from ECF tab)
Combined Multiplier (ECF × TCF)
→ Copy Combined Multiplier to '1-Setup'!B10

## 5-Rough Estimates
Rough Estimates — Token Budget (internal) & AFP Preview (client)
Sprint # | Scenarios | SP Total | FP Total | Tokens Min (K) | Tokens Exp (K) | Tokens Max (K) | Duration Min (d) | Duration Exp (d) | Duration Max (d) | AFP Preview | AFP $ Preview | Phase | Calibration | Notes
1 | 5 | 6.5 | 6.5 | 218 | 436 | 802 | 0.1 | 0.3 | 0.5 | 5.2 | 1300 | Architecture Complete | SEED | Act 0, Act 2
2 | 6 | 8 | 8 | 250 | 504 | 928 | 0.2 | 0.3 | 0.6 | 6.4 | 1600 | Architecture Complete | SEED | Act 2, Act 3
3 | 9 | 7.5 | 7.5 | 206 | 418 | 766 | 0.1 | 0.3 | 0.5 | 6 | 1500 | Architecture Complete | SEED | Act 3, Act 4
4 | 8 | 7.5 | 7.5 | 173 | 360 | 662 | 0.1 | 0.2 | 0.4 | 6 | 1500 | Architecture Complete | SEED | Act 5, Act 6
5 | 10 | 6.5 | 6.5 | 125 | 264 | 482 | 0.1 | 0.2 | 0.3 | 5.2 | 1300 | Architecture Complete | SEED | Act 6, Act 7, Act 8
6 | 7 | 6 | 6 | 141 | 292 | 536 | 0.1 | 0.2 | 0.4 | 4.8 | 1200 | Architecture Complete | SEED | Act 10, Act 8, Act 9
7 | 5 | 12 | 10 | 858 | 1649 | 3083 | 0.6 | 1.1 | 2.1 | 8 | 2000 | Architecture Complete | SEED | Act 11, Act 12, Act 13
8 | 5 | 4 | 4 | 62 | 137 | 252 | 0 | 0.1 | 0.2 | 3.2 | 800 | Architecture Complete | SEED | Act 13, Act 14, Act 15
PROJECT TOTAL | 55 | 58 | 56 | 2033 | 4060 | 7511 | 1.4 | 2.7 | 5 | 44.8 | 11200

## 6-Monte Carlo
Monte Carlo Simulation — P50 / P80 / P95 Forecasts
SIMULATION PARAMETERS
Iterations | 10000
Scenarios (from Scenario List) | 55
Distribution Type | Triangular
Sprint Dependency | Sequential (sprint-by-sprint)
Daily Throughput (K tokens) | 1500
Combined Multiplier (internal) | 0.87
Stack Factor (client) | 1
Org Factor (client) | 0.8
$/FP Rate | 250
SIMULATION RESULTS (run VBA macro: Alt+F8 → RunMonteCarloSimulation)
Percentile | Probability | Token Budget (K) | Token Budget ($) | Duration (days) | AFP (client) | Quote Total ($)
P10 | 10% | 3248 | 10 | 2.2 | 35.8 | 8960
P50 — Median | 50% | 4060 | 12 | 2.7 | 44.8 | 11200
P80 — Planning Target ★ | 80% | 5075 | 15 | 3.4 | 56 | 14000
P95 — Conservative Commitment | 95% | 6090 | 18 | 4.1 | 67.2 | 16800
EBS SIMULATION DATA — 100-percentile probability distribution (10,000 iterations · triangular dist · 56 scenarios)
# | Probability (%) | Token Budget (K) | Duration (days)
1 | 1 | 4804.6 | 3.2
2 | 2 | 4890.5 | 3.26
3 | 3 | 4938.2 | 3.29
4 | 4 | 4973 | 3.32
5 | 5 | 5001.2 | 3.33
6 | 6 | 5033.1 | 3.36
7 | 7 | 5053.8 | 3.37
8 | 8 | 5074.6 | 3.38
9 | 9 | 5095.3 | 3.4
10 | 10 | 5113.3 | 3.41
11 | 11 | 5132.2 | 3.42
12 | 12 | 5149.4 | 3.43
13 | 13 | 5165.8 | 3.44
14 | 14 | 5180.7 | 3.45
15 | 15 | 5197.5 | 3.47
16 | 16 | 5210.3 | 3.47
17 | 17 | 5224.3 | 3.48
18 | 18 | 5234.4 | 3.49
19 | 19 | 5246.4 | 3.5
20 | 20 | 5258.6 | 3.51
21 | 21 | 5271.6 | 3.51
22 | 22 | 5284.3 | 3.52
23 | 23 | 5297.3 | 3.53
24 | 24 | 5308.5 | 3.54
25 | 25 | 5317.8 | 3.55
26 | 26 | 5328.2 | 3.55
27 | 27 | 5337.2 | 3.56
28 | 28 | 5350.2 | 3.57
29 | 29 | 5361.3 | 3.57
30 | 30 | 5371.2 | 3.58
31 | 31 | 5381.7 | 3.59
32 | 32 | 5390.6 | 3.59
33 | 33 | 5400.9 | 3.6
34 | 34 | 5408.9 | 3.61
35 | 35 | 5420.1 | 3.61
36 | 36 | 5429.4 | 3.62
37 | 37 | 5438.9 | 3.63
38 | 38 | 5447.4 | 3.63
39 | 39 | 5456.3 | 3.64
40 | 40 | 5464.9 | 3.64
41 | 41 | 5476.2 | 3.65
42 | 42 | 5485.2 | 3.66
43 | 43 | 5494.8 | 3.66
44 | 44 | 5505.3 | 3.67
45 | 45 | 5514.3 | 3.68
46 | 46 | 5524.5 | 3.68
47 | 47 | 5533.6 | 3.69
48 | 48 | 5544.5 | 3.7
49 | 49 | 5553.6 | 3.7
50 | 50 | 5564.3 | 3.71
51 | 51 | 5575.7 | 3.72
52 | 52 | 5583.8 | 3.72
53 | 53 | 5594.2 | 3.73
54 | 54 | 5603.2 | 3.74
55 | 55 | 5614.6 | 3.74
56 | 56 | 5625.8 | 3.75
57 | 57 | 5636.5 | 3.76
58 | 58 | 5645.1 | 3.76
59 | 59 | 5654.5 | 3.77
60 | 60 | 5664.4 | 3.78
61 | 61 | 5675.5 | 3.78
62 | 62 | 5688.2 | 3.79
63 | 63 | 5697.1 | 3.8
64 | 64 | 5707.6 | 3.81
65 | 65 | 5720.5 | 3.81
66 | 66 | 5730 | 3.82
67 | 67 | 5741.8 | 3.83
68 | 68 | 5753.4 | 3.84
69 | 69 | 5764.4 | 3.84
70 | 70 | 5777.8 | 3.85
71 | 71 | 5788.6 | 3.86
72 | 72 | 5800.1 | 3.87
73 | 73 | 5812.6 | 3.88
74 | 74 | 5824.2 | 3.88
75 | 75 | 5837.7 | 3.89
76 | 76 | 5850.9 | 3.9
77 | 77 | 5863.3 | 3.91
78 | 78 | 5874.7 | 3.92
79 | 79 | 5888.9 | 3.93
80 | 80 | 5902.9 | 3.94
81 | 81 | 5918.1 | 3.95
82 | 82 | 5935.1 | 3.96
83 | 83 | 5951.6 | 3.97
84 | 84 | 5969.7 | 3.98
85 | 85 | 5983.3 | 3.99
86 | 86 | 6001 | 4
87 | 87 | 6017.7 | 4.01
88 | 88 | 6035.8 | 4.02
89 | 89 | 6056 | 4.04
90 | 90 | 6075.5 | 4.05
91 | 91 | 6102 | 4.07
92 | 92 | 6124.8 | 4.08
93 | 93 | 6148.8 | 4.1
94 | 94 | 6176.6 | 4.12
95 | 95 | 6209.4 | 4.14
96 | 96 | 6243.8 | 4.16
97 | 97 | 6294.3 | 4.2
98 | 98 | 6353 | 4.24
99 | 99 | 6444 | 4.3
100 | 100 | 6842.9 | 4.56

## 7-WBS Features
Work Breakdown Structure — BPE-01 Estimation Mode (Django + HTMX · EST-06)
Scenario ID | Feature | Sprint | WP# | Artifact | Type | Flag | Reuse× | K Min | K Exp | K Max | Notes
ACT0-AUTH-01 | authentication.feature | 1 | 1 | Impl plan: login/logout/session | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 2 | User + Session model (accounts) | Model | EXTEND | 0.6 | 4.8 | 9 | 16.8 | BPE-01 est. mode · Model · EXTEND
ACT0-AUTH-01 | authentication.feature | 1 | 3 | AuthRepository | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 4 | AuthService (login, logout, validate) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 5 | LoginView, LogoutView, SessionView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 6 | login.html, session_expired.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 7 | Unit tests: auth flow + edge cases | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 8 | Feature acceptance: auth scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
ACT0-AUTH-01 | authentication.feature | 1 | 10 | E2E: login/logout Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 63.8 | 126 | 240.8 | L1=39K L2=126K Δ=+223% ⚠ >30%
ACT0-NAV-01 | navigation.feature | 1 | 1 | Impl plan: nav + breadcrumbs | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT0-NAV-01 | navigation.feature | 1 | 2 | base.html nav partial + HTMX | Partial | NEW | 1 | 4 | 8 | 15 | BPE-01 est. mode · Partial · NEW
ACT0-NAV-01 | navigation.feature | 1 | 3 | breadcrumb.html, global_search partial | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ACT0-NAV-01 | navigation.feature | 1 | 4 | Template render tests | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT0-NAV-01 | navigation.feature | 1 | 5 | Feature acceptance: nav scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT0-NAV-01 | navigation.feature | 1 | 6 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 38 | 73 | 140 | L1=10K L2=73K Δ=+630% ⚠ >30%
ACT0-ONBOARD-01 | onboarding.feature | 1 | 1 | Impl plan: first-run wizard | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 2 | OnboardingState model | Model | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · Model · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 3 | OnboardingService (wizard steps) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 4 | OnboardingWizardView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 5 | onboarding_step_1.html … step_N.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 6 | Unit tests: wizard state machine | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 7 | Feature acceptance: onboarding | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
ACT0-ONBOARD-01 | onboarding.feature | 1 | 9 | E2E: first-run setup Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 62 | 122 | 232 | L1=39K L2=122K Δ=+213% ⚠ >30%
PB-LIST-01 | playbooks-list-find | 1 | 1 | Impl plan: playbooks list + search | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PB-LIST-01 | playbooks-list-find | 1 | 2 | Playbook model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-LIST-01 | playbooks-list-find | 1 | 3 | PlaybookRepo.list(), search(), filter() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
PB-LIST-01 | playbooks-list-find | 1 | 4 | PlaybookService.list_for_user() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
PB-LIST-01 | playbooks-list-find | 1 | 5 | PlaybookListView + search/filter HTMX | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PB-LIST-01 | playbooks-list-find | 1 | 6 | playbook_list.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
PB-LIST-01 | playbooks-list-find | 1 | 7 | playbook_row.html, filter_form.html | Partial | NEW | 1 | 4 | 8 | 15 | BPE-01 est. mode · Partial · NEW
PB-LIST-01 | playbooks-list-find | 1 | 8 | Unit: list, search, filter, paginate | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PB-LIST-01 | playbooks-list-find | 1 | 9 | Feature acceptance: list scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PB-LIST-01 | playbooks-list-find | 1 | 10 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
PB-LIST-01 | playbooks-list-find | 1 | 11 | E2E: playbooks list Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 60.2 | 118.3 | 225.4 | L1=174K L2=118K Δ=-32% ⚠ >30%
PB-CREATE-01 | playbooks-create | 1 | 1 | Impl plan (review existing) | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
PB-CREATE-01 | playbooks-create | 1 | 2 | Playbook model (done) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-CREATE-01 | playbooks-create | 1 | 3 | PlaybookRepo.create() (done) | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
PB-CREATE-01 | playbooks-create | 1 | 4 | PlaybookService.create() (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
PB-CREATE-01 | playbooks-create | 1 | 5 | PlaybookCreateView wizard (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
PB-CREATE-01 | playbooks-create | 1 | 6 | playbook_create_step_*.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
PB-CREATE-01 | playbooks-create | 1 | 7 | 25/25 tests passing (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
PB-CREATE-01 | playbooks-create | 1 | 8 | Feature acceptance (done) | FAT | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · FAT · REUSE
PB-CREATE-01 | playbooks-create | 1 | 9 | DoD checklist (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
PB-CREATE-01 | playbooks-create | 1 | 10 | E2E Playwright (done) | E2E | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · E2E · REUSE
[8 empty] | 20.1 | 39.6 | 75.6 | L1=174K L2=40K Δ=-77% ⚠ >30%
PB-VIEW-01 | playbooks-view | 2 | 1 | Impl plan: playbook detail view | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PB-VIEW-01 | playbooks-view | 2 | 2 | Playbook model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-VIEW-01 | playbooks-view | 2 | 3 | PlaybookRepo.get_by_id() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
PB-VIEW-01 | playbooks-view | 2 | 4 | PlaybookService.get_detail() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
PB-VIEW-01 | playbooks-view | 2 | 5 | PlaybookDetailView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
PB-VIEW-01 | playbooks-view | 2 | 6 | playbook_detail.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
PB-VIEW-01 | playbooks-view | 2 | 7 | Unit: detail view, 404 handling | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PB-VIEW-01 | playbooks-view | 2 | 8 | Feature acceptance: view scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PB-VIEW-01 | playbooks-view | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
PB-VIEW-01 | playbooks-view | 2 | 10 | E2E: playbook detail Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 53.8 | 105.5 | 201.6 | L1=174K L2=106K Δ=-39% ⚠ >30%
PB-EDIT-01 | playbooks-edit | 2 | 1 | Impl plan: playbook edit form | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PB-EDIT-01 | playbooks-edit | 2 | 2 | Playbook model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-EDIT-01 | playbooks-edit | 2 | 3 | PlaybookRepo.update() (extend create) | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
PB-EDIT-01 | playbooks-edit | 2 | 4 | PlaybookService.update() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
PB-EDIT-01 | playbooks-edit | 2 | 5 | PlaybookEditView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
PB-EDIT-01 | playbooks-edit | 2 | 6 | playbook_edit.html (reuse create form) | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PB-EDIT-01 | playbooks-edit | 2 | 7 | Unit: edit validation, partial save | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PB-EDIT-01 | playbooks-edit | 2 | 8 | Feature acceptance: edit scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PB-EDIT-01 | playbooks-edit | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
PB-EDIT-01 | playbooks-edit | 2 | 10 | E2E: edit playbook Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 50.6 | 99.1 | 189.6 | L1=39K L2=99K Δ=+154% ⚠ >30%
PB-DELETE-01 | playbooks-delete | 2 | 1 | Impl plan: playbook delete modal | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PB-DELETE-01 | playbooks-delete | 2 | 2 | Playbook model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-DELETE-01 | playbooks-delete | 2 | 3 | PlaybookRepo.delete() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
PB-DELETE-01 | playbooks-delete | 2 | 4 | PlaybookService.delete() + cascade | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
PB-DELETE-01 | playbooks-delete | 2 | 5 | PlaybookDeleteView + confirm modal | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
PB-DELETE-01 | playbooks-delete | 2 | 6 | delete_confirm_modal.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PB-DELETE-01 | playbooks-delete | 2 | 7 | Unit: delete + cascade cleanup | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PB-DELETE-01 | playbooks-delete | 2 | 8 | Feature acceptance: delete scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PB-DELETE-01 | playbooks-delete | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 44.6 | 87.1 | 167.6 | L1=39K L2=87K Δ=+123% ⚠ >30%
PB-VERSION-01 | playbooks-versioning | 2 | 1 | Impl plan: playbook versioning | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 2 | PlaybookVersion model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PB-VERSION-01 | playbooks-versioning | 2 | 3 | VersionRepo.create(), list(), diff() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 4 | VersioningService (branch, tag, restore) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 5 | VersionListView, VersionDiffView | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 6 | version_list.html, version_diff.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 7 | Unit: version create, restore, diff | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 8 | Feature acceptance: versioning | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
PB-VERSION-01 | playbooks-versioning | 2 | 10 | E2E: versioning workflow Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 61.4 | 121.5 | 232.4 | L1=174K L2=122K Δ=-30% ⚠ >30%
WF-LIST-01 | workflows-list-find | 2 | 1 | Impl plan: workflows list | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-LIST-01 | workflows-list-find | 2 | 2 | Workflow model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-LIST-01 | workflows-list-find | 2 | 3 | WorkflowRepo.list_for_playbook() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
WF-LIST-01 | workflows-list-find | 2 | 4 | WorkflowService.list() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
WF-LIST-01 | workflows-list-find | 2 | 5 | WorkflowListView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
WF-LIST-01 | workflows-list-find | 2 | 6 | workflow_list.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
WF-LIST-01 | workflows-list-find | 2 | 7 | Unit: list view with playbook context | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-LIST-01 | workflows-list-find | 2 | 8 | Feature acceptance: list scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-LIST-01 | workflows-list-find | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 47.8 | 93.5 | 179.6 | L1=39K L2=94K Δ=+140% ⚠ >30%
WF-CREATE-01 | workflows-create | 2 | 1 | Impl plan: workflow create | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-CREATE-01 | workflows-create | 2 | 2 | Workflow model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-CREATE-01 | workflows-create | 2 | 3 | WorkflowRepo.create() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
WF-CREATE-01 | workflows-create | 2 | 4 | WorkflowService.create() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
WF-CREATE-01 | workflows-create | 2 | 5 | WorkflowCreateView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
WF-CREATE-01 | workflows-create | 2 | 6 | workflow_create.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
WF-CREATE-01 | workflows-create | 2 | 7 | Unit: create + validation | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-CREATE-01 | workflows-create | 2 | 8 | Feature acceptance: create scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-CREATE-01 | workflows-create | 2 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 44.6 | 87.1 | 167.6 | L1=39K L2=87K Δ=+123% ⚠ >30%
WF-VIEW-01 | workflows-view | 3 | 1 | Impl plan: workflow detail | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-VIEW-01 | workflows-view | 3 | 2 | Workflow model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-VIEW-01 | workflows-view | 3 | 3 | WorkflowRepo.get_with_activities() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
WF-VIEW-01 | workflows-view | 3 | 4 | WorkflowService.get_detail() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
WF-VIEW-01 | workflows-view | 3 | 5 | WorkflowDetailView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
WF-VIEW-01 | workflows-view | 3 | 6 | workflow_detail.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
WF-VIEW-01 | workflows-view | 3 | 7 | Unit: detail + nested activities | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-VIEW-01 | workflows-view | 3 | 8 | Feature acceptance: view scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-VIEW-01 | workflows-view | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 47.8 | 93.5 | 179.6 | L1=174K L2=94K Δ=-46% ⚠ >30%
WF-EDIT-01 | workflows-edit | 3 | 1 | Impl plan: workflow edit | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-EDIT-01 | workflows-edit | 3 | 2 | Workflow model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-EDIT-01 | workflows-edit | 3 | 3 | WorkflowRepo.update() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
WF-EDIT-01 | workflows-edit | 3 | 4 | WorkflowService.update() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
WF-EDIT-01 | workflows-edit | 3 | 5 | WorkflowEditView (extend create) | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
WF-EDIT-01 | workflows-edit | 3 | 6 | workflow_edit.html (reuse create) | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
WF-EDIT-01 | workflows-edit | 3 | 7 | Unit: edit validation | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-EDIT-01 | workflows-edit | 3 | 8 | Feature acceptance: edit scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-EDIT-01 | workflows-edit | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 43.1 | 84.1 | 161.6 | L1=10K L2=84K Δ=+741% ⚠ >30%
WF-DELETE-01 | workflows-delete | 3 | 1 | Impl plan: workflow delete | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-DELETE-01 | workflows-delete | 3 | 2 | Workflow model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-DELETE-01 | workflows-delete | 3 | 3 | WorkflowRepo.delete() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
WF-DELETE-01 | workflows-delete | 3 | 4 | WorkflowService.delete() + cascade | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
WF-DELETE-01 | workflows-delete | 3 | 5 | WorkflowDeleteView (reuse PB modal) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
WF-DELETE-01 | workflows-delete | 3 | 6 | delete_confirm_modal (reuse PB) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
WF-DELETE-01 | workflows-delete | 3 | 7 | Unit: delete cascade to activities | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-DELETE-01 | workflows-delete | 3 | 8 | Feature acceptance: delete scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-DELETE-01 | workflows-delete | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 38.9 | 75.7 | 146 | L1=10K L2=76K Δ=+657% ⚠ >30%
WF-EXPORT-01 | workflows-export-import | 3 | 1 | Impl plan: workflow export/import | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 2 | Workflow + related models (exist) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
WF-EXPORT-01 | workflows-export-import | 3 | 3 | WorkflowExportService (JSON serialise) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 4 | WorkflowImportService (validate + save) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 5 | ExportView, ImportView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 6 | export_modal.html, import_modal.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 7 | Unit: export round-trip, import errors | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 8 | Feature acceptance: export/import | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
WF-EXPORT-01 | workflows-export-import | 3 | 10 | E2E: download + re-import Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 64.4 | 129.5 | 247.4 | L1=174K L2=130K Δ=-26%
PH-LIST-01 | phases-list-find | 3 | 1 | Impl plan: phases list | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PH-LIST-01 | phases-list-find | 3 | 2 | Phase model (exists via WF) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PH-LIST-01 | phases-list-find | 3 | 3 | PhaseRepo.list_for_workflow() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PH-LIST-01 | phases-list-find | 3 | 4 | PhaseService.list() | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PH-LIST-01 | phases-list-find | 3 | 5 | PhaseListView + URL | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PH-LIST-01 | phases-list-find | 3 | 6 | phase_list.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PH-LIST-01 | phases-list-find | 3 | 7 | Unit: list phases in workflow ctx | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PH-LIST-01 | phases-list-find | 3 | 8 | Feature acceptance: list | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PH-LIST-01 | phases-list-find | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 52.2 | 103.1 | 198.4 | L1=10K L2=103K Δ=+931% ⚠ >30%
PH-CREATE-01 | phases-create | 3 | 1 | Impl plan: phase create | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PH-CREATE-01 | phases-create | 3 | 2 | Phase model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PH-CREATE-01 | phases-create | 3 | 3 | PhaseRepo.create() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PH-CREATE-01 | phases-create | 3 | 4 | PhaseService.create() | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PH-CREATE-01 | phases-create | 3 | 5 | PhaseCreateView + URL | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PH-CREATE-01 | phases-create | 3 | 6 | phase_create.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PH-CREATE-01 | phases-create | 3 | 7 | Unit: create + order | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PH-CREATE-01 | phases-create | 3 | 8 | Feature acceptance: create | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PH-CREATE-01 | phases-create | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 52.2 | 103.1 | 198.4 | L1=10K L2=103K Δ=+931% ⚠ >30%
PH-VIEW-01 | phases-view | 3 | 1 | Impl plan: phase detail | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PH-VIEW-01 | phases-view | 3 | 2 | Phase model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
PH-VIEW-01 | phases-view | 3 | 3 | PhaseRepo.get_with_activities() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PH-VIEW-01 | phases-view | 3 | 4 | PhaseService.get_detail() | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PH-VIEW-01 | phases-view | 3 | 5 | PhaseDetailView + URL | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PH-VIEW-01 | phases-view | 3 | 6 | phase_detail.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PH-VIEW-01 | phases-view | 3 | 7 | Unit: detail view | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PH-VIEW-01 | phases-view | 3 | 8 | Feature acceptance: view | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PH-VIEW-01 | phases-view | 3 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 52.2 | 103.1 | 198.4 | L1=10K L2=103K Δ=+931% ⚠ >30%
PH-EDIT-01 | phases-edit | 3 | 1 | Impl plan: phase edit | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PH-EDIT-01 | phases-edit | 3 | 2 | PhaseRepo.update() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PH-EDIT-01 | phases-edit | 3 | 3 | PhaseService.update() | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PH-EDIT-01 | phases-edit | 3 | 4 | PhaseEditView (extend create) | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PH-EDIT-01 | phases-edit | 3 | 5 | phase_edit.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PH-EDIT-01 | phases-edit | 3 | 6 | Unit: edit validation | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PH-EDIT-01 | phases-edit | 3 | 7 | Feature acceptance: edit | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PH-EDIT-01 | phases-edit | 3 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 49.8 | 98.6 | 190 | L1=10K L2=99K Δ=+886% ⚠ >30%
PH-DELETE-01 | phases-delete | 3 | 1 | Impl plan: phase delete | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PH-DELETE-01 | phases-delete | 3 | 2 | PhaseRepo.delete() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PH-DELETE-01 | phases-delete | 3 | 3 | PhaseService.delete() + reorder | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PH-DELETE-01 | phases-delete | 3 | 4 | PhaseDeleteView (reuse modal) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
PH-DELETE-01 | phases-delete | 3 | 5 | delete_confirm_modal (reuse) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
PH-DELETE-01 | phases-delete | 3 | 6 | Unit: delete + reorder | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PH-DELETE-01 | phases-delete | 3 | 7 | Feature acceptance: delete | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PH-DELETE-01 | phases-delete | 3 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 43.2 | 85.4 | 165.6 | L1=10K L2=85K Δ=+754% ⚠ >30%
ACT-LIST-01 | activities-list-find | 4 | 1 | Impl plan: activities list | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT-LIST-01 | activities-list-find | 4 | 2 | Activity model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
ACT-LIST-01 | activities-list-find | 4 | 3 | ActivityRepo.list_for_phase() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
ACT-LIST-01 | activities-list-find | 4 | 4 | ActivityService.list() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
ACT-LIST-01 | activities-list-find | 4 | 5 | ActivityListView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ACT-LIST-01 | activities-list-find | 4 | 6 | activity_list.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ACT-LIST-01 | activities-list-find | 4 | 7 | activity_row.html HTMX partial | Partial | NEW | 1 | 4 | 8 | 15 | BPE-01 est. mode · Partial · NEW
ACT-LIST-01 | activities-list-find | 4 | 8 | Unit: list, search, filter | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT-LIST-01 | activities-list-find | 4 | 9 | Feature acceptance: list | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT-LIST-01 | activities-list-find | 4 | 10 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 51.8 | 101.5 | 194.6 | L1=174K L2=102K Δ=-42% ⚠ >30%
ACT-CREATE-01 | activities-create | 4 | 1 | Impl plan: activity create | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT-CREATE-01 | activities-create | 4 | 2 | ActivityRepo.create() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
ACT-CREATE-01 | activities-create | 4 | 3 | ActivityService.create() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
ACT-CREATE-01 | activities-create | 4 | 4 | ActivityCreateView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ACT-CREATE-01 | activities-create | 4 | 5 | activity_create.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
ACT-CREATE-01 | activities-create | 4 | 6 | Unit: create + required fields | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT-CREATE-01 | activities-create | 4 | 7 | Feature acceptance: create | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT-CREATE-01 | activities-create | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 42.2 | 82.6 | 159.2 | L1=39K L2=83K Δ=+112% ⚠ >30%
ACT-VIEW-01 | activities-view | 4 | 1 | Impl plan: activity detail | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT-VIEW-01 | activities-view | 4 | 2 | ActivityRepo.get_with_artifacts() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
ACT-VIEW-01 | activities-view | 4 | 3 | ActivityService.get_detail() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
ACT-VIEW-01 | activities-view | 4 | 4 | ActivityDetailView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ACT-VIEW-01 | activities-view | 4 | 5 | activity_detail.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
ACT-VIEW-01 | activities-view | 4 | 6 | Unit: detail + nested artifacts | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT-VIEW-01 | activities-view | 4 | 7 | Feature acceptance: view | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT-VIEW-01 | activities-view | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 42.2 | 82.6 | 159.2 | L1=39K L2=83K Δ=+112% ⚠ >30%
ACT-EDIT-01 | activities-edit | 4 | 1 | Impl plan: activity edit | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT-EDIT-01 | activities-edit | 4 | 2 | ActivityRepo.update() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
ACT-EDIT-01 | activities-edit | 4 | 3 | ActivityService.update() | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
ACT-EDIT-01 | activities-edit | 4 | 4 | ActivityEditView (reuse create) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
ACT-EDIT-01 | activities-edit | 4 | 5 | activity_edit.html (reuse create) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
ACT-EDIT-01 | activities-edit | 4 | 6 | Unit: edit validation | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT-EDIT-01 | activities-edit | 4 | 7 | Feature acceptance: edit | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT-EDIT-01 | activities-edit | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 34.1 | 65.8 | 127.1 | L1=10K L2=66K Δ=+558% ⚠ >30%
ACT-DELETE-01 | activities-delete | 4 | 1 | Impl plan: activity delete | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ACT-DELETE-01 | activities-delete | 4 | 2 | ActivityRepo.delete() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
ACT-DELETE-01 | activities-delete | 4 | 3 | ActivityService.delete() | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
ACT-DELETE-01 | activities-delete | 4 | 4 | ActivityDeleteView (reuse modal) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
ACT-DELETE-01 | activities-delete | 4 | 5 | delete_confirm_modal (reuse) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
ACT-DELETE-01 | activities-delete | 4 | 6 | Unit: delete | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ACT-DELETE-01 | activities-delete | 4 | 7 | Feature acceptance: delete | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ACT-DELETE-01 | activities-delete | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 34.1 | 65.8 | 127.1 | L1=10K L2=66K Δ=+558% ⚠ >30%
ART-LIST-01 | artifacts-list-find | 4 | 1 | Impl plan: artifacts list | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-LIST-01 | artifacts-list-find | 4 | 2 | Artifact model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
ART-LIST-01 | artifacts-list-find | 4 | 3 | ArtifactRepo.list_for_activity() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
ART-LIST-01 | artifacts-list-find | 4 | 4 | ArtifactService.list() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
ART-LIST-01 | artifacts-list-find | 4 | 5 | ArtifactListView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ART-LIST-01 | artifacts-list-find | 4 | 6 | artifact_list.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
ART-LIST-01 | artifacts-list-find | 4 | 7 | Unit: list by activity | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-LIST-01 | artifacts-list-find | 4 | 8 | Feature acceptance: list | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-LIST-01 | artifacts-list-find | 4 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 44.6 | 87.1 | 167.6 | L1=39K L2=87K Δ=+123% ⚠ >30%
ART-CREATE-01 | artifacts-create | 4 | 1 | Impl plan: artifact create | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-CREATE-01 | artifacts-create | 4 | 2 | ArtifactRepo.create() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
ART-CREATE-01 | artifacts-create | 4 | 3 | ArtifactService.create() | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
ART-CREATE-01 | artifacts-create | 4 | 4 | ArtifactCreateView + URL | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
ART-CREATE-01 | artifacts-create | 4 | 5 | artifact_create.html | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
ART-CREATE-01 | artifacts-create | 4 | 6 | Unit: create | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-CREATE-01 | artifacts-create | 4 | 7 | Feature acceptance: create | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-CREATE-01 | artifacts-create | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 34.1 | 65.8 | 127.1 | L1=10K L2=66K Δ=+558% ⚠ >30%
ART-VIEW-01 | artifacts-view | 4 | 1 | Impl plan: artifact detail | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-VIEW-01 | artifacts-view | 4 | 2 | ArtifactRepo.get_with_inputs() | Repo | EXTEND | 0.6 | 3 | 6 | 12 | BPE-01 est. mode · Repo · EXTEND
ART-VIEW-01 | artifacts-view | 4 | 3 | ArtifactService.get_detail() | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
ART-VIEW-01 | artifacts-view | 4 | 4 | ArtifactDetailView + URL | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ART-VIEW-01 | artifacts-view | 4 | 5 | artifact_detail.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
ART-VIEW-01 | artifacts-view | 4 | 6 | Unit: detail + input listing | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-VIEW-01 | artifacts-view | 4 | 7 | Feature acceptance: view | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-VIEW-01 | artifacts-view | 4 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 42.2 | 82.6 | 159.2 | L1=39K L2=83K Δ=+112% ⚠ >30%
ART-EDIT-01 | artifacts-edit | 5 | 1 | Impl plan: artifact edit | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-EDIT-01 | artifacts-edit | 5 | 2 | ArtifactRepo.update() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
ART-EDIT-01 | artifacts-edit | 5 | 3 | ArtifactService.update() | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
ART-EDIT-01 | artifacts-edit | 5 | 4 | ArtifactEditView (reuse create) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
ART-EDIT-01 | artifacts-edit | 5 | 5 | artifact_edit.html (reuse create) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
ART-EDIT-01 | artifacts-edit | 5 | 6 | Unit: edit | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-EDIT-01 | artifacts-edit | 5 | 7 | Feature acceptance: edit | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-EDIT-01 | artifacts-edit | 5 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 34.1 | 65.8 | 127.1 | L1=10K L2=66K Δ=+558% ⚠ >30%
ART-DELETE-01 | artifacts-delete | 5 | 1 | Impl plan: artifact delete | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-DELETE-01 | artifacts-delete | 5 | 2 | ArtifactRepo.delete() | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
ART-DELETE-01 | artifacts-delete | 5 | 3 | ArtifactService.delete() | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
ART-DELETE-01 | artifacts-delete | 5 | 4 | ArtifactDeleteView (reuse modal) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
ART-DELETE-01 | artifacts-delete | 5 | 5 | delete_confirm_modal (reuse) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
ART-DELETE-01 | artifacts-delete | 5 | 6 | Unit: delete | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-DELETE-01 | artifacts-delete | 5 | 7 | Feature acceptance: delete | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-DELETE-01 | artifacts-delete | 5 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 34.1 | 65.8 | 127.1 | L1=10K L2=66K Δ=+558% ⚠ >30%
ART-FLOW-01 | artifacts-flow | 5 | 1 | Impl plan: artifact upload/download flow | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ART-FLOW-01 | artifacts-flow | 5 | 2 | ArtifactInput model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
ART-FLOW-01 | artifacts-flow | 5 | 3 | ArtifactRepo.attach_file(), get_file() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
ART-FLOW-01 | artifacts-flow | 5 | 4 | ArtifactFlowService (upload, validate) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
ART-FLOW-01 | artifacts-flow | 5 | 5 | ArtifactUploadView, DownloadView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
ART-FLOW-01 | artifacts-flow | 5 | 6 | artifact_upload.html + progress HTMX | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ART-FLOW-01 | artifacts-flow | 5 | 7 | Unit: upload validate, download serving | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ART-FLOW-01 | artifacts-flow | 5 | 8 | Feature acceptance: artifact flow | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ART-FLOW-01 | artifacts-flow | 5 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
ART-FLOW-01 | artifacts-flow | 5 | 10 | E2E: file upload + download Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 61.4 | 121.5 | 232.4 | L1=174K L2=122K Δ=-30% ⚠ >30%
AG-LIST-01 | agents-list-find | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
AG-LIST-01 | agents-list-find | 5 | 2 | Agent (done) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
AG-LIST-01 | agents-list-find | 5 | 3 | AgentListView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
AG-LIST-01 | agents-list-find | 5 | 4 | agent_list.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
AG-LIST-01 | agents-list-find | 5 | 5 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
AG-LIST-01 | agents-list-find | 5 | 6 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 12 | 23.1 | 44.1 | L1=10K L2=23K Δ=+131% ⚠ >30%
AG-CREATE-01 | agents-create | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
AG-CREATE-01 | agents-create | 5 | 2 | AgentRepo (done) | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
AG-CREATE-01 | agents-create | 5 | 3 | AgentService (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
AG-CREATE-01 | agents-create | 5 | 4 | AgentCreateView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
AG-CREATE-01 | agents-create | 5 | 5 | agent_create.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
AG-CREATE-01 | agents-create | 5 | 6 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
AG-CREATE-01 | agents-create | 5 | 7 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 13.5 | 27 | 52.2 | L1=10K L2=27K Δ=+170% ⚠ >30%
AG-VIEW-01 | agents-view | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
AG-VIEW-01 | agents-view | 5 | 2 | AgentDetailView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
AG-VIEW-01 | agents-view | 5 | 3 | agent_detail.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
AG-VIEW-01 | agents-view | 5 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
AG-VIEW-01 | agents-view | 5 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
AG-EDIT-01 | agents-edit | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
AG-EDIT-01 | agents-edit | 5 | 2 | AgentEditView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
AG-EDIT-01 | agents-edit | 5 | 3 | agent_edit.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
AG-EDIT-01 | agents-edit | 5 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
AG-EDIT-01 | agents-edit | 5 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
AG-DELETE-01 | agents-delete | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
AG-DELETE-01 | agents-delete | 5 | 2 | AgentDeleteView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
AG-DELETE-01 | agents-delete | 5 | 3 | delete_modal (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
AG-DELETE-01 | agents-delete | 5 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
AG-DELETE-01 | agents-delete | 5 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
SK-LIST-01 | skills-list-find | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-LIST-01 | skills-list-find | 5 | 2 | Skill (done) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
SK-LIST-01 | skills-list-find | 5 | 3 | SkillListView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-LIST-01 | skills-list-find | 5 | 4 | skill_list.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-LIST-01 | skills-list-find | 5 | 5 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-LIST-01 | skills-list-find | 5 | 6 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 12 | 23.1 | 44.1 | L1=10K L2=23K Δ=+131% ⚠ >30%
SK-CREATE-01 | skills-create | 5 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-CREATE-01 | skills-create | 5 | 2 | SkillRepo (done) | Repo | REUSE | 0.3 | 1.5 | 3 | 6 | BPE-01 est. mode · Repo · REUSE
SK-CREATE-01 | skills-create | 5 | 3 | SkillService (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
SK-CREATE-01 | skills-create | 5 | 4 | SkillCreateView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-CREATE-01 | skills-create | 5 | 5 | skill_create.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-CREATE-01 | skills-create | 5 | 6 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-CREATE-01 | skills-create | 5 | 7 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 13.5 | 27 | 52.2 | L1=10K L2=27K Δ=+170% ⚠ >30%
SK-VIEW-01 | skills-view | 6 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-VIEW-01 | skills-view | 6 | 2 | SkillDetailView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-VIEW-01 | skills-view | 6 | 3 | skill_detail.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-VIEW-01 | skills-view | 6 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-VIEW-01 | skills-view | 6 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
SK-EDIT-01 | skills-edit | 6 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-EDIT-01 | skills-edit | 6 | 2 | SkillEditView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-EDIT-01 | skills-edit | 6 | 3 | skill_edit.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-EDIT-01 | skills-edit | 6 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-EDIT-01 | skills-edit | 6 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
SK-DELETE-01 | skills-delete | 6 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-DELETE-01 | skills-delete | 6 | 2 | SkillDeleteView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-DELETE-01 | skills-delete | 6 | 3 | delete_modal (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-DELETE-01 | skills-delete | 6 | 4 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-DELETE-01 | skills-delete | 6 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 9.6 | 18.6 | 35.7 | L1=10K L2=19K Δ=+86% ⚠ >30%
SK-LINK-01 | skills-link | 6 | 1 | Review existing | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
SK-LINK-01 | skills-link | 6 | 2 | SkillLinkService (done via MCP) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
SK-LINK-01 | skills-link | 6 | 3 | LinkSkillView (done) | View | REUSE | 0.3 | 1.8 | 3.6 | 6.6 | BPE-01 est. mode · View · REUSE
SK-LINK-01 | skills-link | 6 | 4 | link_skill.html (done) | Template | REUSE | 0.3 | 2.4 | 4.8 | 9 | BPE-01 est. mode · Template · REUSE
SK-LINK-01 | skills-link | 6 | 5 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
SK-LINK-01 | skills-link | 6 | 6 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 12 | 24 | 46.2 | L1=39K L2=24K Δ=-38% ⚠ >30%
PIP-CREATE-01 | pips-create | 6 | 1 | Impl plan: PIP create | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PIP-CREATE-01 | pips-create | 6 | 2 | PIP model (new entity) | Model | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · Model · NEW
PIP-CREATE-01 | pips-create | 6 | 3 | PIPRepo.create(), list() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PIP-CREATE-01 | pips-create | 6 | 4 | PIPService.create() + notification | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PIP-CREATE-01 | pips-create | 6 | 5 | PIPCreateView + URL | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PIP-CREATE-01 | pips-create | 6 | 6 | pip_create.html | Template | EXTEND | 0.6 | 4.8 | 9.6 | 18 | BPE-01 est. mode · Template · EXTEND
PIP-CREATE-01 | pips-create | 6 | 7 | Unit: create + validate | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PIP-CREATE-01 | pips-create | 6 | 8 | Feature acceptance: create PIP | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PIP-CREATE-01 | pips-create | 6 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 57.8 | 113.6 | 218 | L1=10K L2=114K Δ=+1036% ⚠ >30%
PIP-MANAGE-01 | pips-manage | 6 | 1 | Impl plan: PIP review workflow | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
PIP-MANAGE-01 | pips-manage | 6 | 2 | PIPRepo.approve(), reject(), list() | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
PIP-MANAGE-01 | pips-manage | 6 | 3 | PIPService.review() + apply changes | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
PIP-MANAGE-01 | pips-manage | 6 | 4 | PIPReviewView, PIPListView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
PIP-MANAGE-01 | pips-manage | 6 | 5 | pip_list.html, pip_review.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
PIP-MANAGE-01 | pips-manage | 6 | 6 | Journey: PIP create→review→apply | Journey | NEW | 1 | 5 | 10 | 18 | BPE-01 est. mode · Journey · NEW
PIP-MANAGE-01 | pips-manage | 6 | 7 | Unit: approve + reject + apply | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
PIP-MANAGE-01 | pips-manage | 6 | 8 | Feature acceptance: PIP management | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
PIP-MANAGE-01 | pips-manage | 6 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
PIP-MANAGE-01 | pips-manage | 6 | 10 | E2E: end-to-end PIP workflow | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 64 | 127 | 242 | L1=39K L2=127K Δ=+226% ⚠ >30%
IE-01 | import-export | 6 | 1 | Impl plan: import/export | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
IE-01 | import-export | 6 | 2 | ExportService (full playbook JSON) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
IE-01 | import-export | 6 | 3 | ImportService (validate + restore) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
IE-01 | import-export | 6 | 4 | ExportView, ImportView + URLs | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
IE-01 | import-export | 6 | 5 | import_export.html + progress HTMX | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
IE-01 | import-export | 6 | 6 | Unit: export round-trip, import errors | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
IE-01 | import-export | 6 | 7 | Feature acceptance: import/export | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
IE-01 | import-export | 6 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
IE-01 | import-export | 6 | 9 | E2E: export + import Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 62 | 125 | 239 | L1=174K L2=125K Δ=-28%
FAM-01 | family-management | 7 | 1 | Impl plan: family management | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
FAM-01 | family-management | 7 | 2 | Family + Membership models (new) | Model | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · Model · NEW
FAM-01 | family-management | 7 | 3 | FamilyRepo (create, invite, manage) | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
FAM-01 | family-management | 7 | 4 | FamilyService (roles, access control) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
FAM-01 | family-management | 7 | 5 | FamilyListView, InviteView, ManageView | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
FAM-01 | family-management | 7 | 6 | family_list.html, invite.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
FAM-01 | family-management | 7 | 7 | Unit: family CRUD + permissions | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
FAM-01 | family-management | 7 | 8 | Feature acceptance: family scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
FAM-01 | family-management | 7 | 9 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
FAM-01 | family-management | 7 | 10 | E2E: family invite + accept Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 67 | 132 | 252 | L1=174K L2=132K Δ=-24%
SYNC-01 | sync-scenarios | 7 | 1 | Impl plan: sync engine | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
SYNC-01 | sync-scenarios | 7 | 2 | SyncState, SyncLog models (new) | Model | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · Model · NEW
SYNC-01 | sync-scenarios | 7 | 3 | SyncRepo (state, conflict, history) | Repo | NEW | 1 | 5 | 10 | 20 | BPE-01 est. mode · Repo · NEW
SYNC-01 | sync-scenarios | 7 | 4 | SyncEngine (pull, push, diff) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
SYNC-01 | sync-scenarios | 7 | 5 | ConflictResolver (3-way merge) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
SYNC-01 | sync-scenarios | 7 | 6 | SyncDashboardView, ConflictResolveView | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
SYNC-01 | sync-scenarios | 7 | 7 | sync_dashboard.html + live HTMX updates | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
SYNC-01 | sync-scenarios | 7 | 8 | Unit: clean pull, push, conflict detect | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
SYNC-01 | sync-scenarios | 7 | 9 | Integration: sync round-trip end-to-end | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
SYNC-01 | sync-scenarios | 7 | 10 | Feature acceptance: sync scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
SYNC-01 | sync-scenarios | 7 | 11 | Journey: sync → conflict → resolve | Journey | NEW | 1 | 5 | 10 | 18 | BPE-01 est. mode · Journey · NEW
SYNC-01 | sync-scenarios | 7 | 12 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
SYNC-01 | sync-scenarios | 7 | 13 | E2E: sync workflow Playwright | E2E | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · E2E · NEW
[8 empty] | 90 | 180 | 345 | L1=1088K L2=180K Δ=-83% ⚠ >30%
MCP-BASE-01 | mcp-integration | 7 | 1 | Impl plan: MCP base server review | Plan | EXTEND | 0.6 | 3 | 4.8 | 9 | BPE-01 est. mode · Plan · EXTEND
MCP-BASE-01 | mcp-integration | 7 | 2 | MCP config model (exists) | Model | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · Model · REUSE
MCP-BASE-01 | mcp-integration | 7 | 3 | MCPServer base (extend for new tools) | Service | EXTEND | 0.6 | 4.8 | 10.8 | 21 | BPE-01 est. mode · Service · EXTEND
MCP-BASE-01 | mcp-integration | 7 | 4 | MCP management UI (new) | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
MCP-BASE-01 | mcp-integration | 7 | 5 | mcp_settings.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
MCP-BASE-01 | mcp-integration | 7 | 6 | Unit: MCP server start/stop | Tests | EXTEND | 0.6 | 6 | 12 | 24 | BPE-01 est. mode · Tests · EXTEND
MCP-BASE-01 | mcp-integration | 7 | 7 | Feature acceptance: MCP integration | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
MCP-BASE-01 | mcp-integration | 7 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 41.2 | 81.1 | 154.4 | L1=174K L2=81K Δ=-53% ⚠ >30%
MCP-PB-01 | mcp-playbooks | 7 | 1 | Review MCP playbooks | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
MCP-PB-01 | mcp-playbooks | 7 | 2 | MCP PB tools (done c049341) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
MCP-PB-01 | mcp-playbooks | 7 | 3 | 250 tests passing | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
MCP-PB-01 | mcp-playbooks | 7 | 4 | Feature acceptance (done) | FAT | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · FAT · REUSE
MCP-PB-01 | mcp-playbooks | 7 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 10.2 | 20.1 | 39 | L1=174K L2=20K Δ=-88% ⚠ >30%
MCP-WF-01 | mcp-workflows | 7 | 1 | Review MCP workflows | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
MCP-WF-01 | mcp-workflows | 7 | 2 | MCP WF tools (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
MCP-WF-01 | mcp-workflows | 7 | 3 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
MCP-WF-01 | mcp-workflows | 7 | 4 | Feature acceptance (done) | FAT | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · FAT · REUSE
MCP-WF-01 | mcp-workflows | 7 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 10.2 | 20.1 | 39 | L1=39K L2=20K Δ=-48% ⚠ >30%
MCP-ACT-01 | mcp-activities | 8 | 1 | Review MCP activities | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
MCP-ACT-01 | mcp-activities | 8 | 2 | MCP ACT tools (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
MCP-ACT-01 | mcp-activities | 8 | 3 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
MCP-ACT-01 | mcp-activities | 8 | 4 | Feature acceptance (done) | FAT | REUSE | 0.3 | 2.4 | 4.5 | 8.4 | BPE-01 est. mode · FAT · REUSE
MCP-ACT-01 | mcp-activities | 8 | 5 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 10.2 | 20.1 | 39 | L1=39K L2=20K Δ=-48% ⚠ >30%
MCP-AG-01 | mcp-agents | 8 | 1 | Review MCP agents | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
MCP-AG-01 | mcp-agents | 8 | 2 | MCP AGT tools (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
MCP-AG-01 | mcp-agents | 8 | 3 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
MCP-AG-01 | mcp-agents | 8 | 4 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 7.8 | 15.6 | 30.6 | L1=10K L2=16K Δ=+56% ⚠ >30%
MCP-SK-01 | mcp-skills | 8 | 1 | Review MCP skills | Plan | REUSE | 0.3 | 1.5 | 2.4 | 4.5 | BPE-01 est. mode · Plan · REUSE
MCP-SK-01 | mcp-skills | 8 | 2 | MCP SK tools (done) | Service | REUSE | 0.3 | 2.4 | 5.4 | 10.5 | BPE-01 est. mode · Service · REUSE
MCP-SK-01 | mcp-skills | 8 | 3 | Tests (done) | Tests | REUSE | 0.3 | 3 | 6 | 12 | BPE-01 est. mode · Tests · REUSE
MCP-SK-01 | mcp-skills | 8 | 4 | DoD (done) | DoD | REUSE | 0.3 | 0.9 | 1.8 | 3.6 | BPE-01 est. mode · DoD · REUSE
[8 empty] | 7.8 | 15.6 | 30.6 | L1=39K L2=16K Δ=-60% ⚠ >30%
SET-01 | settings | 8 | 1 | Impl plan: settings page | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
SET-01 | settings | 8 | 2 | UserSettings model (extend accounts) | Model | EXTEND | 0.6 | 4.8 | 9 | 16.8 | BPE-01 est. mode · Model · EXTEND
SET-01 | settings | 8 | 3 | SettingsService (read, update) | Service | NEW | 1 | 8 | 18 | 35 | BPE-01 est. mode · Service · NEW
SET-01 | settings | 8 | 4 | SettingsView + URL | View | NEW | 1 | 6 | 12 | 22 | BPE-01 est. mode · View · NEW
SET-01 | settings | 8 | 5 | settings.html + HTMX auto-save | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
SET-01 | settings | 8 | 6 | Unit: settings save + reload | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
SET-01 | settings | 8 | 7 | Feature acceptance: settings | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
SET-01 | settings | 8 | 8 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 52.8 | 104 | 198.8 | L1=10K L2=104K Δ=+940% ⚠ >30%
ERR-01 | error-recovery | 8 | 1 | Impl plan: error recovery | Plan | NEW | 1 | 5 | 8 | 15 | BPE-01 est. mode · Plan · NEW
ERR-01 | error-recovery | 8 | 2 | Custom 404, 500, 403 handlers + URLs | View | EXTEND | 0.6 | 3.6 | 7.2 | 13.2 | BPE-01 est. mode · View · EXTEND
ERR-01 | error-recovery | 8 | 3 | 404.html, 500.html, error_recovery.html | Template | NEW | 1 | 8 | 16 | 30 | BPE-01 est. mode · Template · NEW
ERR-01 | error-recovery | 8 | 4 | Unit: error page rendering | Tests | NEW | 1 | 10 | 20 | 40 | BPE-01 est. mode · Tests · NEW
ERR-01 | error-recovery | 8 | 5 | Feature acceptance: error scenarios | FAT | NEW | 1 | 8 | 15 | 28 | BPE-01 est. mode · FAT · NEW
ERR-01 | error-recovery | 8 | 6 | DoD checklist | DoD | NEW | 1 | 3 | 6 | 12 | BPE-01 est. mode · DoD · NEW
[8 empty] | 37.6 | 72.2 | 138.2 | L1=39K L2=72K Δ=+85% ⚠ >30%

## 8-Detailed Estimates
Detailed Estimates — BPE-01 L2 vs L1 Cross-Check (EST-06 compliant · update after each sprint close)
Scenario ID | Feature | Sprint | Size | SP | FP | L2 Min(K) | L2 Exp(K) | L2 Max(K) | L1 Exp(K) | L1/L2 Δ% | Actual(K) | Token VF | AFP Est($) | AFP VF | Status | Notes
ACT0-AUTH-01 | authentication.feature | 1 | S | 1 | 1 | 63.8 | 126 | 240.8 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+223% — review sizing
ACT0-NAV-01 | navigation.feature | 1 | XS | 0.5 | 0.5 | 38 | 73 | 140 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+630% — review sizing
ACT0-ONBOARD-01 | onboarding.feature | 1 | S | 1 | 1 | 62 | 122 | 232 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+213% — review sizing
PB-LIST-01 | playbooks-list-find | 1 | M | 2 | 2 | 60.2 | 118.3 | 225.4 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-32% — review sizing
PB-CREATE-01 | playbooks-create | 1 | M | 2 | 2 | 20.1 | 39.6 | 75.6 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-77% — review sizing
PB-VIEW-01 | playbooks-view | 2 | M | 2 | 2 | 53.8 | 105.5 | 201.6 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-39% — review sizing
PB-EDIT-01 | playbooks-edit | 2 | S | 1 | 1 | 50.6 | 99.1 | 189.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+154% — review sizing
PB-DELETE-01 | playbooks-delete | 2 | S | 1 | 1 | 44.6 | 87.1 | 167.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+123% — review sizing
PB-VERSION-01 | playbooks-versioning | 2 | M | 2 | 2 | 61.4 | 121.5 | 232.4 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-30% — review sizing
WF-LIST-01 | workflows-list-find | 2 | S | 1 | 1 | 47.8 | 93.5 | 179.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+140% — review sizing
WF-CREATE-01 | workflows-create | 2 | S | 1 | 1 | 44.6 | 87.1 | 167.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+123% — review sizing
WF-VIEW-01 | workflows-view | 3 | M | 2 | 2 | 47.8 | 93.5 | 179.6 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-46% — review sizing
WF-EDIT-01 | workflows-edit | 3 | XS | 0.5 | 0.5 | 43.1 | 84.1 | 161.6 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+741% — review sizing
WF-DELETE-01 | workflows-delete | 3 | XS | 0.5 | 0.5 | 38.9 | 75.7 | 146 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+657% — review sizing
WF-EXPORT-01 | workflows-export-import | 3 | M | 2 | 2 | 64.4 | 129.5 | 247.4 | 174 |  |  |  | 400 |  | PLANNED | L1/L2 Δ=-26% — acceptable
PH-LIST-01 | phases-list-find | 3 | XS | 0.5 | 0.5 | 52.2 | 103.1 | 198.4 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+931% — review sizing
PH-CREATE-01 | phases-create | 3 | XS | 0.5 | 0.5 | 52.2 | 103.1 | 198.4 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+931% — review sizing
PH-VIEW-01 | phases-view | 3 | XS | 0.5 | 0.5 | 52.2 | 103.1 | 198.4 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+931% — review sizing
PH-EDIT-01 | phases-edit | 3 | XS | 0.5 | 0.5 | 49.8 | 98.6 | 190 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+886% — review sizing
PH-DELETE-01 | phases-delete | 3 | XS | 0.5 | 0.5 | 43.2 | 85.4 | 165.6 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+754% — review sizing
ACT-LIST-01 | activities-list-find | 4 | M | 2 | 2 | 51.8 | 101.5 | 194.6 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-42% — review sizing
ACT-CREATE-01 | activities-create | 4 | S | 1 | 1 | 42.2 | 82.6 | 159.2 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+112% — review sizing
ACT-VIEW-01 | activities-view | 4 | S | 1 | 1 | 42.2 | 82.6 | 159.2 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+112% — review sizing
ACT-EDIT-01 | activities-edit | 4 | XS | 0.5 | 0.5 | 34.1 | 65.8 | 127.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+558% — review sizing
ACT-DELETE-01 | activities-delete | 4 | XS | 0.5 | 0.5 | 34.1 | 65.8 | 127.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+558% — review sizing
ART-LIST-01 | artifacts-list-find | 4 | S | 1 | 1 | 44.6 | 87.1 | 167.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+123% — review sizing
ART-CREATE-01 | artifacts-create | 4 | XS | 0.5 | 0.5 | 34.1 | 65.8 | 127.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+558% — review sizing
ART-VIEW-01 | artifacts-view | 4 | S | 1 | 1 | 42.2 | 82.6 | 159.2 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+112% — review sizing
ART-EDIT-01 | artifacts-edit | 5 | XS | 0.5 | 0.5 | 34.1 | 65.8 | 127.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+558% — review sizing
ART-DELETE-01 | artifacts-delete | 5 | XS | 0.5 | 0.5 | 34.1 | 65.8 | 127.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+558% — review sizing
ART-FLOW-01 | artifacts-flow | 5 | M | 2 | 2 | 61.4 | 121.5 | 232.4 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-30% — review sizing
AG-LIST-01 | agents-list-find | 5 | XS | 0.5 | 0.5 | 12 | 23.1 | 44.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+131% — review sizing
AG-CREATE-01 | agents-create | 5 | XS | 0.5 | 0.5 | 13.5 | 27 | 52.2 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+170% — review sizing
AG-VIEW-01 | agents-view | 5 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
AG-EDIT-01 | agents-edit | 5 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
AG-DELETE-01 | agents-delete | 5 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
SK-LIST-01 | skills-list-find | 5 | XS | 0.5 | 0.5 | 12 | 23.1 | 44.1 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+131% — review sizing
SK-CREATE-01 | skills-create | 5 | XS | 0.5 | 0.5 | 13.5 | 27 | 52.2 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+170% — review sizing
SK-VIEW-01 | skills-view | 6 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
SK-EDIT-01 | skills-edit | 6 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
SK-DELETE-01 | skills-delete | 6 | XS | 0.5 | 0.5 | 9.6 | 18.6 | 35.7 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+86% — review sizing
SK-LINK-01 | skills-link | 6 | S | 1 | 1 | 12 | 24 | 46.2 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=-38% — review sizing
PIP-CREATE-01 | pips-create | 6 | XS | 0.5 | 0.5 | 57.8 | 113.6 | 218 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+1036% — review sizing
PIP-MANAGE-01 | pips-manage | 6 | S | 1 | 1 | 64 | 127 | 242 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+226% — review sizing
IE-01 | import-export | 6 | M | 2 | 2 | 62 | 125 | 239 | 174 |  |  |  | 400 |  | PLANNED | L1/L2 Δ=-28% — acceptable
FAM-01 | family-management | 7 | M | 2 | 2 | 67 | 132 | 252 | 174 |  |  |  | 400 |  | PLANNED | L1/L2 Δ=-24% — acceptable
SYNC-01 | sync-scenarios | 7 | L | 5 | 3 | 90 | 180 | 345 | 1088 |  |  |  | 600 |  | PLANNED | ⚠ L1/L2 Δ=-83% — review sizing
MCP-BASE-01 | mcp-integration | 7 | M | 2 | 2 | 41.2 | 81.1 | 154.4 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-53% — review sizing
MCP-PB-01 | mcp-playbooks | 7 | M | 2 | 2 | 10.2 | 20.1 | 39 | 174 |  |  |  | 400 |  | PLANNED | ⚠ L1/L2 Δ=-88% — review sizing
MCP-WF-01 | mcp-workflows | 7 | S | 1 | 1 | 10.2 | 20.1 | 39 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=-48% — review sizing
MCP-ACT-01 | mcp-activities | 8 | S | 1 | 1 | 10.2 | 20.1 | 39 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=-48% — review sizing
MCP-AG-01 | mcp-agents | 8 | XS | 0.5 | 0.5 | 7.8 | 15.6 | 30.6 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+56% — review sizing
MCP-SK-01 | mcp-skills | 8 | S | 1 | 1 | 7.8 | 15.6 | 30.6 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=-60% — review sizing
SET-01 | settings | 8 | XS | 0.5 | 0.5 | 52.8 | 104 | 198.8 | 10 |  |  |  | 100 |  | PLANNED | ⚠ L1/L2 Δ=+940% — review sizing
ERR-01 | error-recovery | 8 | S | 1 | 1 | 37.6 | 72.2 | 138.2 | 39 |  |  |  | 200 |  | PLANNED | ⚠ L1/L2 Δ=+85% — review sizing
TOTAL |  |  |  |  | 56 | 2084.8 | 4097.9 | 7863.9 | 4060 |  |  |  | 11200