## 0-Client Quote
FORGE Estimation — Client Quote (AFP × $/FP)
A. PRICING PARAMETERS (Stack Factor × Org Factor × $/FP)
Parameter | Value | Description / Source
Stack Factor (base tier) |  | See REFERENCE_TABLE §4: 0.85 (greenfield) → 2.50+ (gov/FedRAMP)
Stack Factor modifiers |  | On-prem +0.10 / Legacy +0.15 / Multi-cloud +0.15 / Mobile +0.20
Stack Factor TOTAL
Org Factor |  | See REFERENCE_TABLE §5: 0.80 (startup) → 3.50 (government)
$/FP Rate | 250 | SEED default $250. Update after 3 sprints via EST-08 calibration.
$/FP Status | SEED | SEED / CALIBRATED — change after 3 sprint actuals
B. QUOTE SUMMARY (AFP = FP × Stack × Org)
Line Item | FP | Stack × Org Adj. | AFP | $ Total (AFP × $/FP)
Sprint 0 — Project Setup (BSP + DSP) | 15
Feature Delivery (from Scenario List)
PROJECT TOTAL
C. DELIVERY COMMITMENT BANDS (from Monte Carlo — EST-07)
Percentile | AFP (adj. for band) | $ Total | Duration (days) | Est. Completion Date
P50 — Median
P80 — Planning Target ★
P95 — Conservative Commitment
D. NOTES
• FP weights: XS=0.5, S=1, M=2, L=3, XL=5 (see REFERENCE_TABLE §1)
• AFP = Σ FP × Stack Factor × Org Factor — this is what the client sees
• $/FP rate starts at $250 SEED. Update via EST-08 after each sprint close.
• ECF / TCF are INTERNAL multipliers (Tab 3-ECF, 4-TCF) — never on this quote
• Delivery bands (section C) are populated after running Monte Carlo (EST-07)

## 1-Setup
FORGE Estimation Template — Setup & Calibration
A. PROJECT PARAMETERS
Project Name
Sprint Duration (days) | 1
Daily Token Throughput (K tokens) | 1500
AI Model | Claude Sonnet 4.x
Productivity Adjustment Factor (PAF) | 1.4
Rework Surcharge (%) | 0.12
Combined Risk Multiplier (ECF × TCF — internal)
Estimation Phase | Approved Concept
Convergence Min Multiplier | 0.5
Convergence Max Multiplier | 2
B. REFERENCE STORY BASELINES (SP = internal effort ¦ FP = client deliverable)
Size | SP (internal) | FP weight (client) | K Min (K tok) | K Exp (K tok) | K Max (K tok) | Status | Source / Notes
XS | 0.5 | 0.5 | 12 | 22 | 36 | SEED | Single HTMX fragment, read-only view
S | 1 | 1 | 25 | 45 | 72 | SEED | Simple CRUD, 1 model, 3-5 scenarios
M | 2 | 2 | 60 | 100 | 160 | SEED | New model+service+repo+view+template
L | 5 | 3 | 155 | 250 | 410 | SEED | Cross-cutting feature (auth, search, export)
XL | 8 | 5 | 275 | 440 | 720 | SEED | Novel integration (external API, MCP server)
SP drives internal token budget (Est. = SP × K × ECF×TCF). FP weights drive client AFP (AFP = Σ FP × Stack × Org). L=5 SP / 3 FP and XL=8 SP / 5 FP — complex work ≠ proportional client value.
C. SPRINT CAPACITY PLANNING
Sprint # | SP Capacity | Token Budget (K, expected) | Token Budget (K, max) | Notes
1
2
3
4
5
6
7
8

## 2-Scenario List
Scenario List — Level 1 T-Shirt Sizing (SP = internal ¦ FP = client)
Scenario ID | Feature | Act/Group | Scenario Description | Size | SP (internal) | FP weight (client) | K Min | K Exp | K Max | Adj K Min | Adj K Exp | Adj K Max | Sprint # | Notes / Assumptions
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
M
TOTALS
Total FP (row 28, col G) → copy to '0-Client Quote'!B15 (Feature Delivery FP) to compute AFP.

## 3-ECF
Environmental Complexity Factors (ECF) — INTERNAL
INTERNAL: ECF feeds the internal combined multiplier (token budget). Never shown to client.
# | Factor | Weight | Rating (0–5) | Weighted | Notes
E1 | Familiarity with AI model/tooling | 1.5 | 3
E2 | Part-time participation / context switching | -1 | 3
E3 | Analyst / prompt engineering experience | 0.5 | 3
E4 | Lead developer application experience | 0.5 | 3
E5 | Motivation of team | 1 | 3
E6 | Stability of requirements | 2 | 3
E7 | Part-time users / product owners | -1 | 3
E8 | Difficulty of stack / language | -1 | 3
AI-Specific Extension Factors
A1 | AI model tier (Opus=5, Sonnet=3, Haiku=1) | 0.8 | 3
A2 | Prompt maturity (mature=5, first use=1) | 0.6 | 3
A3 | Hallucination risk (low risk=5, high risk=1) | -0.5 | 3
A4 | Context window pressure (large ctx=5, small=1) | -0.4 | 3
A5 | AI code rework rate (41% baseline = rating 3) | -0.6 | 3
ECF Base
AI Adjustment
ECF Final = Base × AI Adj
→ ECF Final × TCF Final = Combined Multiplier → paste into '1-Setup'!B10

## 4-TCF
Technical Complexity Factors (TCF) — INTERNAL
INTERNAL: TCF feeds the combined multiplier. Client-facing complexity is captured by Stack Factor (Tab 0).
# | Factor | Weight | Rating (0–5) | Weighted | Notes
T1 | Distributed system / microservices | 2 | 3
T2 | Response time / performance requirements | 1 | 3
T3 | End-user efficiency (optimized UX) | 1 | 3
T4 | Complex internal processing / algorithms | 1 | 3
T5 | Code reusability requirement | 1 | 3
T6 | Easy to install / deploy | 0.5 | 3
T7 | Easy to use (usability target) | 0.5 | 3
T8 | Portability across platforms | 2 | 3
T9 | Maintainability / easy to change | 1 | 3
T10 | Concurrent use / multi-user | 1 | 3
T11 | Security features | 1 | 3
T12 | Third-party API / direct access | 1 | 3
T13 | Special user training required | 1 | 3
TCF Final
ECF Final (from ECF tab)
Combined Multiplier (ECF × TCF)
→ Copy Combined Multiplier to '1-Setup'!B10

## 5-Rough Estimates
Rough Estimates — Token Budget (internal) & AFP Preview (client)
Sprint # | Scenarios | SP Total | FP Total | Tokens Min (K) | Tokens Exp (K) | Tokens Max (K) | Duration Min (d) | Duration Exp (d) | Duration Max (d) | AFP Preview | AFP $ Preview | Phase | Calibration | Notes
1 | [11 empty] | Approved Concept | SEED
2 | [11 empty] | Approved Concept | SEED
3 | [11 empty] | Approved Concept | SEED
4 | [11 empty] | Approved Concept | SEED
5 | [11 empty] | Approved Concept | SEED
6 | [11 empty] | Approved Concept | SEED
7 | [11 empty] | Approved Concept | SEED
8 | [11 empty] | Approved Concept | SEED
PROJECT TOTAL

## 6-Monte Carlo
Monte Carlo Simulation — P50 / P80 / P95 Forecasts
SIMULATION PARAMETERS
Iterations | 10000
Scenarios (from Scenario List)
Distribution Type | Triangular
Sprint Dependency | Sequential
Daily Throughput (K tokens)
Combined Multiplier (internal)
Stack Factor (client)
Org Factor (client)
$/FP Rate
SIMULATION RESULTS (run VBA macro: Alt+F8 → RunMonteCarloSimulation)
Percentile | Probability | Token Budget (K) | Token Budget ($) | Duration (days) | AFP (client) | Quote Total ($)
P10 | 10%
P50 — Median | 50%
P80 — Planning Target ★ | 80%
P95 — Conservative Commitment | 95%
EBS SIMULATION DATA — 100-percentile probability distribution (populated by EST-07)
# | Probability (%) | Token Budget (K tokens) | Duration (days)

## 7-WBS Features
Work Breakdown Structure — Function Point Decomposition (BPE-01 per feature)
Scenario ID | Feature | Sprint | Work Package # | Artifact (from BPE-01 Plan) | BPE Activity | Reuse Flag | Reuse Mult. | WP Min (K) | WP Exp (K) | WP Max (K) | Adj Min | Adj Exp | Adj Max | Notes
← Run BPE-01 (Plan Feature) in estimation mode for each scenario. BPE-01 produces the artifact list; enter one row per artifact here. Do NOT pre-fill — every feature has a different artifact set.
SCENARIO TOTAL

## 8-Detailed Estimates
Detailed Estimates — FP Decomposition Aggregates & Actuals
Scenario ID | Feature | Sprint | Size | SP (internal) | FP weight (client) | FP Decomp Min (K) | FP Decomp Exp (K) | FP Decomp Max (K) | L1 Exp (K) | L1/L2 Delta % | Actual Tokens (K) | Token VF | AFP Est. | AFP VF | Status | Notes
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
|  |  | M | [11 empty] | PLANNED
PROJECT TOTAL