## 1-Setup
FORGE Estimation Template — Setup & Calibration
A. PROJECT PARAMETERS
Project Name
Sprint Duration (days) | 1
Daily Token Throughput (K tokens) | 1500
AI Model | Claude Sonnet 4.x
Productivity Adjustment Factor (PAF) | 1.4
Rework Surcharge (%) | 0.12
Combined Risk Multiplier (from ECF×TCF)
Estimation Phase | Approved Concept
Convergence Min Multiplier | 0.5
Convergence Max Multiplier | 2
B. REFERENCE STORY K-TOKEN BASELINES (tokens per story point)
Size | SP Value | K Min (K tok) | K Expected (K tok) | K Max (K tok) | Status | Source / Notes
XS | 0.5 | 15 | 25 | 40 | SEED | Simple read-only view
S | 1 | 30 | 50 | 80 | SEED | Single CRUD, 1 model, 3-5 scenarios
M | 2 | 70 | 110 | 180 | SEED | 2 models, service layer, 6-10 scenarios
L | 5 | 180 | 290 | 480 | SEED | Multi-model, integrations, 10-15 scenarios
XL | 8 | 320 | 520 | 850 | SEED | Complex subsystem, external API, >15 scenarios
C. SPRINT CAPACITY PLANNING
Sprint # | SP Capacity | Token Budget (K, expected) | Token Budget (K, max) | Notes
1 |  | 0 | 0
2 |  | 0 | 0
3 |  | 0 | 0
4 |  | 0 | 0
5 |  | 0 | 0
6 |  | 0 | 0
7 |  | 0 | 0
8 |  | 0 | 0

## 2-Scenario List
Scenario List — Level 1 T-Shirt Sizing
Scenario ID | Feature | Act/Group | Scenario Description | Size (XS/S/M/L/XL) | SP Value | K Min | K Exp | K Max | Adj K Min | Adj K Exp | Adj K Max | Sprint # | Notes / Assumptions
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
|  |  |  | M | 2 | 70 | 110 | 180 | 0 | 0 | 0
TOTALS |  |  |  |  | 30 |  |  |  | 0 | 0 | 0

## 3-ECF
Environmental Complexity Factors (ECF)
# | Factor | Weight | Rating (0–5) | Weighted | Notes
E1 | Familiarity with AI model/tooling | 1.5 | 3 | 4.5
E2 | Part-time participation / context switching | -1 | 3 | -3
E3 | Analyst / prompt engineering experience | 0.5 | 3 | 1.5
E4 | Lead developer application experience | 0.5 | 3 | 1.5
E5 | Motivation of team | 1 | 3 | 3
E6 | Stability of requirements | 2 | 3 | 6
E7 | Part-time users / product owners | -1 | 3 | -3
E8 | Difficulty of stack / language | -1 | 3 | -3
AI-Specific Extension Factors
A1 | AI model tier (Opus=5, Sonnet=3, Haiku=1) | 0.8 | 3 | 2.4
A2 | Prompt maturity (mature=5, first use=1) | 0.6 | 3 | 1.8
A3 | Hallucination risk (low=5, high=1) | -0.5 | 3 | -1.5
A4 | Context window pressure (large=5, small=1) | -0.4 | 3 | -1.2
A5 | AI code rework rate (41% baseline = rating 3) | -0.6 | 3 | -1.8
ECF Base |  | 1.175
AI Adjustment |  | 0.985
ECF Final = Base × AI Adj |  | 1.1574
→ Paste ECF Final value into '1-Setup'!B10 combined multiplier cell after multiplying by TCF Final

## 4-TCF
Technical Complexity Factors (TCF)
# | Factor | Weight | Rating (0–5) | Weighted | Notes
T1 | Distributed system / microservices | 2 | 3 | 6
T2 | Response time / performance requirements | 1 | 3 | 3
T3 | End-user efficiency (optimized UX) | 1 | 3 | 3
T4 | Complex internal processing / algorithms | 1 | 3 | 3
T5 | Code reusability requirement | 1 | 3 | 3
T6 | Easy to install / deploy | 0.5 | 3 | 1.5
T7 | Easy to use (usability target) | 0.5 | 3 | 1.5
T8 | Portability across platforms | 2 | 3 | 6
T9 | Maintainability / easy to change | 1 | 3 | 3
T10 | Concurrent use / multi-user | 1 | 3 | 3
T11 | Security features | 1 | 3 | 3
T12 | Third-party API / direct access | 1 | 3 | 3
T13 | Special user training required | 1 | 3 | 3
TCF Final |  | 1.02
ECF Final (from ECF tab) |  | 1.1574
Combined Multiplier (ECF × TCF) |  | 1.1805
→ Copy Combined Multiplier to '1-Setup'!B10

## 5-Rough Estimates
Rough Estimates — Level 1 Token Budget & Duration
Sprint # | Scenarios (count) | SP Total | Tokens Min (K) | Tokens Exp (K) | Tokens Max (K) | Duration Min (days) | Duration Exp (days) | Duration Max (days) | Phase | Calibration | Cumul Tokens Exp (K) | Notes
1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
8 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | Approved Concept | SEED | 0
PROJECT TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 6-Monte Carlo
Monte Carlo Simulation — P50 / P80 / P95 Forecasts
SIMULATION PARAMETERS
Iterations | 10000
Scenarios (from Scenario List) | 0
Distribution Type | Triangular
Sprint Dependency | Sequential
Daily Throughput (K tokens) | 1500
Combined Multiplier | 0
SIMULATION RESULTS (run VBA macro: Alt+F8 → RunMonteCarloSimulation)
Percentile | Probability | Token Budget (K) | Token Budget ($) | Duration (days) | Est. Completion Date
P10 | 10%
P50 — Median | 50%
P80 — Planning Target ★ | 80%
P95 — Conservative Commitment | 95%
EBS CHART — Release Date Certainty (auto-populated by VBA macro)
The VBA macro will generate two S-curve charts here: Curve 1: Token Budget Certainty (x = K tokens, y = probability of completion) Curve 2: Duration Certainty (x = calendar date, y = probability of on-time delivery) To run the simulation manually without VBA: 1. Copy Scenario List PERT triplets (cols G, H, I) to a simulation tool 2. Use =NORM.INV(RAND(), expected, (max-min)/6) for each scenario 3. Sum 10,000 samples per iteration 4. Sort totals ascending and read off P50, P80, P95 positions

## 7-WBS Features
Work Breakdown Structure — Level 2 Decomposition (requires SAO.md)
Scenario ID | Feature | Sprint | Work Package # | Artifact Type | BPE Activity | Reuse Flag | Reuse Mult. | WP Min (K) | WP Exp (K) | WP Max (K) | Adj Min | Adj Exp | Adj Max
|  |  | WP-01 | Django Model + Admin | BPE-02 | NEW | 1 | 10 | 15 | 25 | 10 | 15 | 25
|  |  | WP-02 | Repository Methods | BPE-02 | NEW | 1 | 6 | 10 | 16 | 6 | 10 | 16
|  |  | WP-03 | Service Layer | BPE-02 | NEW | 1 | 12 | 18 | 30 | 12 | 18 | 30
|  |  | WP-04 | Django View + URL | BPE-02 | NEW | 1 | 8 | 12 | 20 | 8 | 12 | 20
|  |  | WP-05 | Unit + Integration Tests | BPE-02 | NEW | 1 | 13 | 20 | 33 | 13 | 20 | 33
|  |  | WP-06 | Django Template + HTMX | BPE-03 | NEW | 1 | 10 | 16 | 26 | 10 | 16 | 26
|  |  | WP-07 | Template Partials | BPE-03 | NEW | 1 | 5 | 8 | 13 | 5 | 8 | 13
|  |  | WP-08 | Feature Acceptance Tests | BPE-04 | NEW | 1 | 9 | 14 | 23 | 9 | 14 | 23
|  |  | WP-09 | Journey Certification Tests | BPE-05 | NEW | 1 | 6 | 10 | 16 | 6 | 10 | 16
|  |  | WP-10 | DoD Checklist Review | BPE-06 | NEW | 1 | 4 | 6 | 10 | 4 | 6 | 10
|  |  | WP-11 | E2E Tests + PR | BPE-07 | NEW | 1 | 7 | 11 | 18 | 7 | 11 | 18
|  |  | WP-12 | Implementation Plan | BPE-01 | NEW | 1 | 5 | 8 | 13 | 5 | 8 | 13
|  |  | SCENARIO TOTAL | [7 empty] | 95 | 148 | 243

## 8-Detailed Estimates
Detailed Estimates — Level 2 Scenario Aggregates & Actuals
Scenario ID | Feature | Sprint | Size | SP | L2 Min (K) | L2 Exp (K) | L2 Max (K) | L1 Exp (K) | L1/L2 Delta % | Actual Tokens (K) | Velocity Factor | Status | Confidence | Notes
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
|  |  | M | 2 | [7 empty] | PLANNED | SEED
PROJECT TOTAL |  |  |  |  | 0 | 0 | 0 | 0 |  | 0